## Slide 1
Health Performance Council
Country Health SA’s Aboriginal Community & Consumer Engagement Strategy— A post-implementation review
World-wide web seminar

## Slide 2: Acknowledgement
We acknowledge all the Aboriginal peoples of South Australia, the complexity and diversity of their communities and that each has its own beliefs and practices. We recognise their cultural authority and respect their enduring spiritual relationship with their countries.
We are grateful to everyone who helped us with this review by giving so generously of their time, knowledge and experience.

## Slide 3: Housekeeping
This seminar will be recorded and published on our world-wide web site

## Slide 4: Housekeeping
This seminar will be recorded and published on our world-wide web site
Cellphones off or silent, please
Cellphones off or silent, please

## Slide 5: Housekeeping
This seminar will be recorded and published on our world-wide web site
Cellphones off or silent, please
Please mute your microphone unless speaking
Please mute your microphone unless speaking

## Slide 6: Housekeeping
This seminar will be recorded and published on our world-wide web site
Cellphones off or silent, please
Please mute your microphone unless speaking
In event of emergency alarm, follow your local procedures
Questions will be taken at the end

## Slide 7: Your host
Professor Lisa Jackson Pulver am
Western Sydney University
Pro Vice-Chancellor, Engagement
Pro Vice-Chancellor, Aboriginal & Torres Strait Islander Leadership
Provost, Paramatta South
University of Sydney (from Oct 2018)
Deputy Vice-Chancellor
Health Performance Council
Member since 2012

## Slide 8: Seminar outline
About the Health Performance Council
Background to this review
What we did
What we found
Our advice
Questions and discussion

## Slide 9: The Health Performance Council
Statutory body under Health Care Act 2008.
Advice to the Minister for Health on performance of the health system, health outcomes for South Australians, and community and individual engagement effectiveness.
Publish four-yearly reviews of South Australian health system performance, case studies and other monitoring reports.

## Slide 10: Background

## Slide 11: Context
The Strategy
Launched by Country Health in May 2015
Aims ‘to assist [Country Health] implement culturally respectful and meaningful community and consumer engagement strategies’
Context: Country Health’s broader community engagement strategy
Notes: Country Health’s broader ‘Consumer and Community Engagement Strategy’ was also published in May 2015, following the SA Health policy for all LHN Chief Executive’s to ‘implement effective consumer engagement system’.

## Slide 12: Context
March 2008
The new Health Care Act provides for the creation of Health Advisory Councils to perform advocacy for their community and to provide advice to and undertake other functions for the health Minister and the health system.
June 2008
41 Health Advisory Councils established for country South Australia.
December 2011
As required by law, Health Performance Council completes a review of the effectiveness and governance of the Health Advisory Councils.
May 2015
Country Health SA releases its overarching Consumer and Community Engagement Strategy.
May 2015
Country Health SA releases its more specific Aboriginal Community & Consumer Engagement Strategy.
March 2016
Health Performance Council decides to revisit its 2011 review of Health Advisory Councils’ governance.
July 2016
Health Performance Council spins off from the revisit review a separate project – the subject of this report – to review the implementation of the Aboriginal Community & Consumer Engagement Strategy.
August 2017
Health Performance Council publishes its revisit review of Health Advisory Councils’ governance, noting and endorsing Country Health SA’s Aboriginal Community & Consumer Engagement Strategy.
By 1999
Seven regional Aboriginal Health Advisory Committees exist as touchpoints of engagement between the health system and Aboriginal community members in country South Australia.
2006
Health system reforms in South Australia; Country Health SA established.
Timeline

## Slide 13: Context
March 2008
The new Health Care Act provides for the creation of Health Advisory Councils to perform advocacy for their community and to provide advice to and undertake other functions for the health Minister and the health system.
June 2008
41 Health Advisory Councils established for country South Australia.
December 2011
As required by law, Health Performance Council completes a review of the effectiveness and governance of the Health Advisory Councils.
May 2015
Country Health SA releases its overarching Consumer and Community Engagement Strategy.
May 2015
Country Health SA releases its more specific Aboriginal Community & Consumer Engagement Strategy.
March 2016
Health Performance Council decides to revisit its 2011 review of Health Advisory Councils’ governance.
July 2016
Health Performance Council spins off from the revisit review a separate project – the subject of this report – to review the implementation of the Aboriginal Community & Consumer Engagement Strategy.
August 2017
Health Performance Council publishes its revisit review of Health Advisory Councils’ governance, noting and endorsing Country Health SA’s Aboriginal Community & Consumer Engagement Strategy.
By 1999
Seven regional Aboriginal Health Advisory Committees exist as touchpoints of engagement between the health system and Aboriginal community members in country South Australia.
2006
Health system reforms in South Australia; Country Health SA established.
March 2008
The new Health Care Act provides for the creation of Health Advisory Councils to perform advocacy for their community and to provide advice to and undertake other functions for the health Minister and the health system.
June 2008
41 Health Advisory Councils established for country South Australia.
December 2011
As required by law, Health Performance Council completes a review of the effectiveness and governance of the Health Advisory Councils.
May 2015
Country Health SA releases its overarching Consumer and Community Engagement Strategy.
May 2015
Country Health SA releases its more specific Aboriginal Community & Consumer Engagement Strategy.
March 2016
Health Performance Council decides to revisit its 2011 review of Health Advisory Councils’ governance.
July 2016
Health Performance Council spins off from the revisit review a separate project – the subject of this report – to review the implementation of the Aboriginal Community & Consumer Engagement Strategy.
August 2017
Health Performance Council publishes its revisit review of Health Advisory Councils’ governance, noting and endorsing Country Health SA’s Aboriginal Community & Consumer Engagement Strategy.
By 1999
Seven regional Aboriginal Health Advisory Committees exist as touchpoints of engagement between the health system and Aboriginal community members in country South Australia.
2006
Health system reforms in South Australia; Country Health SA established.
Timeline

## Slide 14: Context
March 2008
The new Health Care Act provides for the creation of Health Advisory Councils to perform advocacy for their community and to provide advice to and undertake other functions for the health Minister and the health system.
June 2008
41 Health Advisory Councils established for country South Australia.
December 2011
As required by law, Health Performance Council completes a review of the effectiveness and governance of the Health Advisory Councils.
May 2015
Country Health SA releases its overarching Consumer and Community Engagement Strategy.
May 2015
Country Health SA releases its more specific Aboriginal Community & Consumer Engagement Strategy.
March 2016
Health Performance Council decides to revisit its 2011 review of Health Advisory Councils’ governance.
July 2016
Health Performance Council spins off from the revisit review a separate project – the subject of this report – to review the implementation of the Aboriginal Community & Consumer Engagement Strategy.
August 2017
Health Performance Council publishes its revisit review of Health Advisory Councils’ governance, noting and endorsing Country Health SA’s Aboriginal Community & Consumer Engagement Strategy.
By 1999
Seven regional Aboriginal Health Advisory Committees exist as touchpoints of engagement between the health system and Aboriginal community members in country South Australia.
2006
Health system reforms in South Australia; Country Health SA established.
March 2008
The new Health Care Act provides for the creation of Health Advisory Councils to perform advocacy for their community and to provide advice to and undertake other functions for the health Minister and the health system.
June 2008
41 Health Advisory Councils established for country South Australia.
December 2011
As required by law, Health Performance Council completes a review of the effectiveness and governance of the Health Advisory Councils.
May 2015
Country Health SA releases its overarching Consumer and Community Engagement Strategy.
May 2015
Country Health SA releases its more specific Aboriginal Community & Consumer Engagement Strategy.
March 2016
Health Performance Council decides to revisit its 2011 review of Health Advisory Councils’ governance.
July 2016
Health Performance Council spins off from the revisit review a separate project – the subject of this report – to review the implementation of the Aboriginal Community & Consumer Engagement Strategy.
August 2017
Health Performance Council publishes its revisit review of Health Advisory Councils’ governance, noting and endorsing Country Health SA’s Aboriginal Community & Consumer Engagement Strategy.
By 1999
Seven regional Aboriginal Health Advisory Committees exist as touchpoints of engagement between the health system and Aboriginal community members in country South Australia.
2006
Health system reforms in South Australia; Country Health SA established.
Timeline

## Slide 15: Context
Aboriginal people in country South Australia
A third of the state’s population lives in country SA
Half of the Aboriginal population live in country SA
Health inequities
Including earlier death
Based on Australian Bureau of Statistics data, 2018. Extract from database 'B07 Indigenous Status by Age by Sex', ABS.stat, generated 08 August 2018.
Based on Australian Bureau of Statistics data, 2017. 'Statistical Area Level 3 2016 to Primary Health Network 2017', ASGS Geographic Correspondences (2016). ABS Geospatial Solutions.
Notes: All SA population: 29.3% live outside Adelaide metro region.
Aboriginal people: 51.1% live outside Adelaide metro region.
From HPC Aboriginal Health case study (2017) [all of SA]:
High smoking rate (over 1 in 3)
2 in 3 overweight or obese
High prevalence of high blood pressure
Much higher rates than non-Aboriginal people of deaths from heart disease, diabetes, respiratory disease, cancer and self-harm [from Australia-wide stats]
Double the infant and child mortality rate
Median age at death (all Australia):
Aboriginal and Torres Strait Islander: 58.8 years
Non-Indigenous: 82.0 years
[for 2014-16. From ABS 3302.0 ‘Deaths, Australia, 2016’]

## Slide 16: The review

## Slide 17: The review
Objectives
How successful has the Strategy been in influencing change in the short term?
What are the remaining gaps in consumer and community engagement activities that would be expected to achieve the Strategy’s stated aims in the short term?
What are they key and emerging areas for future focus that will improve the chances of achieving medium and long-term outcomes?
Notes: Objectives were determined thanks to Advisory Group [discussed in later methodology slides]

## Slide 18: The review
Governance
Health Performance Council
  Project owner

## Slide 19: The review
Governance
Health Performance Council
Advisory group: co-design, co-production
  Chair: Professor Lisa Jackson Pulver AM, a proud Wiradjuri Koori woman and HPC member
  Aboriginal Health Council of SA
  Council of Aboriginal Elders of SA
  Country Health’s Aboriginal ‘Experts by Experience’
  Country Health executive (Aboriginal Heath Directorate)
  SA Health (Aboriginal Health branch)

## Slide 20: The review
Governance
Health Performance Council
Advisory group
Secretariat: project management and day-to-day operation

## Slide 21: The review
Governance
Health Performance Council
Advisory group
Secretariat: project management and day-to-day operation
External ethical and scientific oversight
  Department for Health and Wellbeing Human Research Ethics Committee
  Considered also by Aboriginal Health Research Ethics Committee – no oversight required

## Slide 22: Methods

## Slide 23: Design
Advisory Group
Co-design; co-production
Experts by Experience at the centre
  Because the Strategy is really about them

## Slide 24: Design
Preliminary work
Determined project specification
Considered impact of project:
  Aboriginal Health Impact Statement
Reflected respectful research considerations:
  SA Aboriginal Health Research Accord

## Slide 25: Design
Studied the Strategy
Found no evidence of any formal ‘theory of change’
Inferred intended outcomes
Developed a logic model
Determined review objectives

## Slide 26: Logic model
SA Aboriginal community members
Stakeholder organisations, e.g., Primary Health Networks
National Safety & Quality Health Standards 2.1 – 2.9
Country Health resources and staff
Aboriginal Community Controlled Health Organisations
Data, e.g., SA Health, ABS
Inputs

## Slide 27: Logic model
Inputs
Individual
Inputs
Strategies (activities)
Directorates / programs and services
Network
Systems
Notes: Individual – Developing engagement activities, centred on the flagship ‘Experts by Experience’ register
Directorates/programs/services – Cultural awareness, staff engagement, boosting staff capacity to engage meaningfully
Network – Cultural awareness, staff engagement, boosting staff capacity to engage meaningfully
Systems – Processes to make for culturally safe services

## Slide 28: Logic model
Individual
Inputs
Strategies (activities)
Outputs
Directorates / programs and services
Network
Systems

## Slide 29: Logic model
Individuals – awareness of how to engage
Individuals – feel supported to engage
Community and consumers participate: Experts by Experience
Staff training and professional development
Staff aware of benefits of engagement
Health services form partnerships that make change and innovate
Inputs
Strategies (activities)
Outputs
Outcomes short-term

## Slide 30: Logic model
Improved Aboriginal consumer experience
More regional Aboriginal participation
Aboriginal Workforce experience
Culturally competent and efficient
Reduced institutional racism
More use by regional SA Aboriginal people
Inputs
Strategies (activities)
Outputs
Outcomes short-term
Outcomes medium-term

## Slide 31: Logic model
Integrated approach to ensure workforce is culturally fit
Improved health outcomes for regional SA Aboriginal people
Ensure data sovereignty and integrity
Increased consumer health literacy.
Inputs
Strategies (activities)
Outputs
Outcomes short-term
Outcomes medium-term
Outcomes long-term

## Slide 32: Review
Design of evidence base
Three-phase ‘mixed methods’ review
  Desktop review
  Stakeholder surveys
  Focus groups
Stakeholders engaged:
  Aboriginal ‘Experts by Experience’ and Youth Council
  Country Health staff – Aboriginal and not
  Country Health executives
  External stakeholder organisations

## Slide 33: Review
Data collection
No routinely collected data
  So we had to commission our own
Expert help needed
  PwC’s Indigenous Consulting
  Skills and validity to do research with the community

## Slide 34: Design
Analysis and reporting
Data reviewed by Aboriginal researchers
Analysed and validated at experts’ workshop
Over-arching HPC report

## Slide 35: The work

## Slide 36: Desktop review
Literature scan (not a systematic review)
Working closely with Country Health staff
  Data trawl
  Document scan
Assessed the data and documents against the Strategy’s intended outcomes and logic model

## Slide 37: Desktop review
Results:
  Some evidence of where there had already been impact and outcomes of the Strategy
  Early assessment of issues and themes to explore
  Information gaps needing to be filled
Stakeholder surveys designed to fill in the data gaps

## Slide 38: Stakeholder surveys
Six different groups
  Aboriginal Experts by Experience
  Aboriginal Youth Council community members
  Country Health staff (Aboriginal)
  Country Health staff (executives)
  Country Health staff (other)
  External stakeholder organisations
Tailored surveys for each group
Total: 147 respondents

## Slide 39: Stakeholder surveys
Response rates generally poor
Group | Responses | 
Staff: Executives | 26% | of 35
External stakeholders | 23% | of 31
Staff: Aboriginal | 16% | of 159
Experts by Experience | 15% | of 168
Aboriginal Youth | 11% | of 35
Staff: Other | < 1% | of 8,764
!

## Slide 40: Focus groups
Design basis:
  Findings from desktop review
  Built upon by findings from stakeholder surveys
  Applied against the logic model
Intent: validate what had been found so far and fill in the gaps
Seven sessions across country South Australia
  Videoconferences at additional sites
Total: 130 participants

## Slide 41: Limitations
Practical and necessary choice not to engage whole of the community
Poor survey responses
Data collection bias:
  Assumption that participants fairly represent all

## Slide 42: Key findings

## Slide 43: The Strategy’s design
Strengths
Strategy is well regarded
And ground-breaking
A model for others to follow

## Slide 44: The Strategy’s design
Weaknesses
We had to make inferences
  Our logic model
  Our list of intended outcomes of the Strategy

## Slide 45: Individual awareness
Strengths
Aboriginal people are more aware of how to engage with the health system

## Slide 46: Individual awareness
Opportunities
more communication/promotion needed to country health staff and external bodies about the Strategy
more engagement needed between country health staff and Aboriginal community to build connections

## Slide 47: Individuals feeling supported
Opportunities
Strategy has had very little effect so far on helping community and consumers feel supported to engage
Aboriginal community perspectives could be more actively involved in health planning and delivery
Poor confidence in Country Health amongst some Aboriginal community and consumers
Needs of Elders and young Aboriginal people poorly understood.

## Slide 48: Participation
Strengths
The Experts by Experience register has improved engagement and individual participation

## Slide 49: Participation
Opportunities
Communications – within Country Health and externally – about the Experts by Experience register needs to improved so that this wonderful resource can be better used
There are not enough Experts by Experience
Training for Experts needs to be reviewed
More clear and sound management of the Experts register could make it more useful

## Slide 50: Workforce
Cultural training is mandatory… but not all staff are doing it!
Estimated that 29 out of every 100 Country Health staff have not completed cultural training

## Slide 51: Outcomes: workforce
Concerns over Aboriginal cultural awareness and competence within Country Health
Cultural competency to be tackled centrally as part of workplace culture

## Slide 52: Outcomes: workforce
Aboriginal staff woefully under-represented in Country Health
Region | Aboriginal population | Aboriginal staff
Eyre and Far North | 12.1% | 1.9%
Flinders and Upper North | 8.7% | 3.4%
Yorke and Northern | 2.3% | 1.1%
Barossa, Hills, Fleurieu | 1.0% | 1.9%
Riverland, Mallee, Coorong | 3.5% | 2.1%
South East | 1.7% | 1.0%

## Slide 53: Workforce
Staff do not properly understand benefits of community engagement
Better governance needed to ensure the Strategy continues to be embedded and meet its aims

## Slide 54: Partnerships
Strategy has had very little effect so far
External stakeholders have not been widely partnered with to engage with Aboriginal consumers
Relationships between Country Health and local organisations need to be strengthened
More decisions need to be made by communities

## Slide 55: Key recommendations

## Slide 56: Recommendations
Opportunities to build partnerships with Aboriginal Community-Controlled Health Organisations
More effective use to be made of the Aboriginal Experts by Experience register
Embed culture of human rights-based and reconciliatory awareness
Target better alignment with national health quality standards

## Slide 57: Recommendations
Strategic work needed to respect regional diversity of Aboriginal people and communities – ways of engagement, program design and delivery
More Aboriginal staff required
Audit systemic racism and take action to eliminate it
Be sure to (continue to) review and evaluate the Strategy

## Slide 58: Recommendations
Strategic work needed to respect regional diversity of Aboriginal people and communities – ways of engagement, program design and delivery
More Aboriginal staff required
Audit systemic racism and take action to eliminate it
Be sure to (continue to) review and evaluate the Strategy

## Slide 59: Recommendations
New health landscape in country South Australia
New LHNs: duty to develop consumer and community engagement strategies
This review is an evidence base
Opportunity for binding agreement on Aboriginal engagement between the centre and the new LHNs

## Slide 60: A personal view

## Slide 61: Klynton Wanganeen
Notes: [0:00]
Good morning, or good afternoon. My name is Klynton Wanganeen - Kandi to those who know me really well, and I'm Kandi to those who don't know me so well.
[0:08]
I just want to say a few words about the review of the Country Health SA's Community & Consumer Engagement Strategy and the importance of it.
[0:19]
I was one of the co-facilitators of the focus groups with PriceWaterhouseCoopers (PIC) Indigenous Consulting firm, and I can say from all of the engagement we've had that the review was very well received, it was important and it really builds on the uniqueness of the Experts by Experience programme that is the centrepiece of the consumer engagement strategy.
[0:49]
For me, I was rapt by the amount of people that were willing to give their personal experiences, because it's those experiences that they've had with the system that leads to the improvement.
[1:04]
Over a considerable amount of time, we went around to various locations and we had the various cohorts, whether we're talking about Aboriginal youth, Aboriginal Elders, Aboriginal staff, staff who've been Experts by Experience as well as working with Aboriginal Experts by Experience, and in a number of locations the Experts by Experience programme works quite well; in other areas it doesn't work so well.
[1:37]
And the review is looking at how it's working well, why it's working well, and then what should be done to improve it so that we have consistency and overall beneficial outcomes for the Aboriginal community.
[1:52]
In some areas where it's not working so well, it could be because there is an Aboriginal Community Controlled system working with the non-Aboriginal system in partnerships. In other areas they don't really have partnerships.
[2:08]
We've had administrators join us in various aspects of the review at a number of sites.
[2:15]
We had multiple video links for some of the focus groups and I can say that everyone who participated was very patient and willing to come forward and have their say to contribute to the review.
[2:30]
The recommendations of the review however is only as important as the implementation: to learn from what works well, to use that information to help others to improve their services and then overall, improve the outcome for Aboriginal peoples.
[2:47]
For me, as an Aboriginal person, I see the applicability of the Experts by Experience programme being able to be rolled out to other government programmes that service Aboriginal people because there's, besides health, quite a number of government services that do not deliver the service appropriately for our people, and it needs our people to co-design and co-deliver.
[3:12]
So for all those Aboriginal people and non-Aboriginal people involved in the review, and to PriceWaterhouseCoopers Indigenous Consulting and the Health Performance Council - who I named last but not least - the collaborative approach for this is important to improve the wellbeing for Aboriginal people.
Thank you very much.
[3:30]

## Slide 62: Conclusions

## Slide 63: Bright spots
Raised awareness of how to engage with health services
Participation by Aboriginal consumers and community members: the Aboriginal Experts by Experience register
Staff training and development

## Slide 64: Opportunities to improve
Aboriginal participation in the workforce
community and consumers feeling supported to engage
strategic relationship with Aboriginal Experts by Experience
governance structures for the Strategy
cultural competence across the network

## Slide 65: Overall
This is a good strategy
But implementation has been patchy
Some good things have flowed from it
But a lot more needs to be done

## Slide 66: Next steps for the review
Final HPC report by end of 2018
Key findings to be incorporated into HPC’s four-yearly review

## Slide 67: Questions and discussion
Artwork: Jordan Lovegrove, Ngarrindjeri, Dreamtime Public Relations